## Project_Analysis
Area | Current Findings
Product | Hotel/hospitality management system for hotel owner/manager operations
Frontend | React 18, Vite, React Router, React Icons, Recharts used in dashboard/housekeeping
Backend | Node.js, Express, MySQL/MySQL2, bcryptjs, JWT dependency present, CORS
Current Running Backend | `backend/server.js` exposes only `/register` and `/login` with plaintext password flow
Scaffolded Backend | Route/controller files exist for admin, users, hotels, rooms, bookings, reviews, dashboard, but most are empty or not wired
Database | No migrations/schema files in repo; code references `users`, `admins`, `hotels`, `rooms`, `bookings`
Auth | Frontend currently uses `localStorage`; backend has separate incomplete auth implementations
Integrations | Avatar image service, local image assets, MySQL planned, Google login button UI only
User Roles | Guest/customer, hotel owner/manager, staff, admin implied
Testing | No test framework or tests found
Deployment | No CI/CD, environment examples, Docker, hosting config, or production build pipeline found

## Feature_Breakdown
Feature | Page | Module | Components | Current State | Main Gap
Registration | `/` | Authentication | Register form, validation, Google button UI | Frontend localStorage prototype | Backend API integration, hashing, validation, duplicate checks
Login | `/login` | Authentication | Login form, password toggle, staff login UI | Frontend localStorage prototype | JWT/session auth, role routing, protected routes
Owner Dashboard | `/dashboard` | Dashboard | KPI cards, occupancy chart, revenue chart, activities, recent bookings, room status, reviews, subscription | Static/prototype data | API-driven metrics, date filters, real revenue/booking data
Booking Popup | Dashboard modal | Bookings | Step 1 customer info | Incomplete multi-step flow | Finish booking/payment/confirmation steps and persist booking
Rooms | `/rooms` and dashboard tab | Room Management | Room grid, pagination, add/edit/delete, details modal, gallery | Local state CRUD | Room APIs, image upload, validation, status sync
Customers | Dashboard tab | CRM | Customer table, stats, add/edit/delete modal | Local state CRUD | Customer APIs, consistent customer fields, search/filter/export
Check-in/out | `/checkinout` and dashboard tab | Front Desk | Guest table, filters, check-in/check-out forms | Local state workflow | Booking lookup, room status update, billing dependency
Housekeeping | `/housekeeping` and dashboard tab | Operations | Stats, charts, room cleaning list, staff tasks | Static data | Task assignment, status update APIs, staff linkage
Maintenance | `/maintenance` and dashboard tab | Operations | Critical issues, requests, technicians, workload, calendar | Static data | Request lifecycle APIs, assignment, SLA tracking
Reviews | Dashboard modal | Reputation | Rating summary, tags, reviews list | Static data | Review APIs, moderation, source linkage
Staff/Departments/Attendance | Sidebar only | Staff Management | Navigation labels | Not implemented | Full pages, APIs, tables, permissions
Billing/Reports/Revenue | Sidebar only | Finance | Navigation labels and dashboard revenue chart | Mostly not implemented | Billing, invoices, reports, export, analytics
Subscription | Dashboard card | SaaS Plan | Basic/Premium toggle | Local state only | Plan table, payment integration, entitlement gates

## Complete_Roadmap
Task ID | Project | Page | Module | Submodule | Task Description | Frontend Work | Backend Work | Database Work | API Work | Testing Work | Priority | Estimated Hours | Start Date | Target Date | Dependencies | Risk Level | Current Status | Completion % | Owner | Expected Output
SH-001 | StayHub | All | Architecture | Repo audit | Baseline current frontend/backend/database state | Document current gaps | Review server/routes/controllers | Identify referenced tables | List missing endpoints | Manual smoke review | High | 3 | 2026-06-23 | 2026-06-23 | None | Low | Done | 100 | Solution Architect | Current-state assessment completed
SH-002 | StayHub | Backend | Architecture | Server wiring | Refactor backend server to use route modules | None | Wire routes, env config, error middleware | None | Expose versioned API base | Smoke test endpoints | Critical | 5 | 2026-06-23 | 2026-06-24 | SH-001 | High | Planned | 0 | Backend Developer | Stable Express API shell
SH-003 | StayHub | Database | Core Schema | Schema design | Create normalized MySQL schema | None | Map entities and relationships | Create migrations for users, hotels, rooms, bookings, customers, housekeeping, maintenance, reviews, invoices | None | Validate migration execution | Critical | 8 | 2026-06-24 | 2026-06-25 | SH-002 | High | Planned | 0 | Database Engineer | Database schema and migrations
SH-004 | StayHub | Auth | Register/Login | Authentication API | Replace localStorage auth with backend auth | Connect forms to API | Implement bcrypt register/login and JWT | Users/admins/staff tables | POST auth/register, POST auth/login | Manual and API validation | Critical | 8 | 2026-06-25 | 2026-06-26 | SH-003 | High | Planned | 0 | Full Stack Developer | Secure login and registration
SH-005 | StayHub | All | Auth | Protected routes | Add role-based route protection | Add auth context and guards | JWT middleware | User role columns | GET auth/me | Route access testing | Critical | 5 | 2026-06-26 | 2026-06-27 | SH-004 | High | Planned | 0 | Full Stack Developer | Protected owner/staff/admin routes
SH-006 | StayHub | Dashboard | Analytics | KPI integration | Connect dashboard KPIs to backend | Replace hardcoded stats | Aggregate booking, room, revenue queries | Indexes on booking date/status | GET dashboard/summary | API and UI smoke tests | High | 6 | 2026-06-27 | 2026-06-29 | SH-003 | Medium | Planned | 0 | Full Stack Developer | Live dashboard metrics
SH-007 | StayHub | Rooms | Room Management | Room CRUD | Persist room management | Add filters, add/edit/delete modal, detail view and pagination | Create room CRUD controller | Rooms and room_images tables | GET/POST/PUT/DELETE rooms | CRUD validation tests | Critical | 10 | 2026-06-29 | 2026-07-01 | SH-003 | High | In Progress | 35 | Full Stack Developer | Room CRUD connected to DB
SH-008 | StayHub | Rooms | Room Management | Gallery and amenities | Persist room gallery and amenities | Add room-type gallery, thumbnails, image slider and amenities modal | Implement gallery/amenities logic | room_images, amenities, room_amenities | GET/POST room assets | Manual modal testing | Medium | 6 | 2026-07-01 | 2026-07-02 | SH-007 | Medium | In Progress | 65 | Frontend Developer | Room details with persisted amenities
SH-009 | StayHub | Bookings | Booking Flow | Multi-step popup | Complete booking wizard steps | Add booking, room, payment, confirmation steps | Booking creation logic | bookings, booking_guests, payments | POST bookings | Wizard validation tests | Critical | 12 | 2026-07-02 | 2026-07-04 | SH-004, SH-007 | High | Planned | 0 | Full Stack Developer | Complete booking creation flow
SH-010 | StayHub | Bookings | Booking List | Recent bookings | Create bookings page/list from real data | Add filters, status badges, actions | Booking list query | booking indexes | GET bookings | Manual list tests | High | 8 | 2026-07-04 | 2026-07-06 | SH-009 | Medium | Planned | 0 | Full Stack Developer | Manage bookings from dashboard
SH-011 | StayHub | Customers | CRM | Customer CRUD | Persist customers module | Add overview cards, filter panel, customer modal, edit/delete and age/city autofill | Customer controller | customers table | GET/POST/PUT/DELETE customers | CRUD tests | High | 8 | 2026-07-06 | 2026-07-08 | SH-003 | Medium | In Progress | 55 | Full Stack Developer | Customer management persisted
SH-012 | StayHub | Check-in/out | Front Desk | Check-in workflow | Connect check-in to booking and room status | Add guest table, status filters, guest detail/edit modal and check-in form | Update booking and room status | booking_events table | POST checkins | Workflow tests | Critical | 10 | 2026-07-08 | 2026-07-10 | SH-009, SH-007 | High | In Progress | 45 | Full Stack Developer | Check-in updates booking and room
SH-013 | StayHub | Check-in/out | Front Desk | Check-out workflow | Connect check-out to billing and room status | Add checkout form, payment validation and checked-out status transition | invoices/payments linkage | POST checkouts | Workflow tests | Critical | 10 | 2026-07-10 | 2026-07-12 | SH-012 | High | In Progress | 40 | Full Stack Developer | Check-out with payment guard
SH-014 | StayHub | Housekeeping | Operations | Task assignment | Add assign/update housekeeping task flow | Add status overview, clickable status distribution, manual SVG trend, status summary and room task list | Housekeeping controller | housekeeping_tasks table | GET/POST/PATCH housekeeping | Manual status tests | High | 9 | 2026-07-13 | 2026-07-15 | SH-007, SH-013 | Medium | In Progress | 45 | Full Stack Developer | Housekeeping tasks managed
SH-015 | StayHub | Maintenance | Operations | Request lifecycle | Add maintenance CRUD and assignment | Add new request modal and status actions | Maintenance controller | maintenance_requests table | GET/POST/PATCH maintenance | Manual request tests | High | 9 | 2026-07-15 | 2026-07-17 | SH-003 | Medium | Planned | 0 | Full Stack Developer | Maintenance workflow persisted
SH-016 | StayHub | Reviews | Reputation | Review management | Persist review list and rating summaries | Connect modal to API | Review controller | reviews table | GET/POST reviews | Manual filter tests | Medium | 5 | 2026-07-17 | 2026-07-18 | SH-003 | Low | Planned | 0 | Full Stack Developer | Review dashboard from database
SH-017 | StayHub | Staff | Staff Management | Staff pages | Implement staff, departments, attendance pages | Create sidebar routes/pages | Staff controllers | staff, departments, attendance tables | Staff CRUD and attendance APIs | Manual page tests | High | 16 | 2026-07-20 | 2026-07-24 | SH-005 | Medium | Planned | 0 | Full Stack Developer | Staff management module
SH-018 | StayHub | Finance | Billing | Invoices and payments | Implement billing page and invoices | Add invoice UI, payment statuses | Billing controller | invoices, payments tables | Billing APIs | Billing workflow tests | High | 14 | 2026-07-24 | 2026-07-29 | SH-009, SH-013 | High | Planned | 0 | Full Stack Developer | Billing module ready
SH-019 | StayHub | Reports | Reports | Revenue reports | Create reports and export views | Add date filters and export buttons | Report aggregation queries | Add indexes for reporting | GET reports/revenue | Report accuracy tests | Medium | 12 | 2026-07-29 | 2026-08-03 | SH-018 | Medium | Planned | 0 | Full Stack Developer | Operational reports and revenue analytics
SH-020 | StayHub | All | UX | Responsive cleanup | Fix layout, encoding, empty states, loading states | Update CSS and copy | None | None | None | Cross-page manual QA | High | 12 | 2026-08-03 | 2026-08-07 | Feature APIs | Medium | Planned | 0 | Frontend Developer | Polished responsive UI
SH-021 | StayHub | Backend | Security | Auth hardening | Add security middleware and validation | Show clear auth errors | Input validation, CORS, rate limiting, JWT expiry | None | All secured endpoints | Security smoke tests | Critical | 10 | 2026-08-10 | 2026-08-12 | SH-005 | High | Planned | 0 | Backend Developer | Secure API baseline
SH-022 | StayHub | All | Testing | Test setup | Add automated test framework | Add component tests where useful | Add API tests | Create test DB seed strategy | Test scripts | Unit/integration tests | Critical | 16 | 2026-08-12 | 2026-08-18 | Core APIs | High | Planned | 0 | QA Lead | Repeatable test suite
SH-023 | StayHub | All | DevOps | Environment setup | Add env examples and config cleanup | Show setup docs | Use dotenv config | DB env variables | None | Start/build smoke tests | High | 6 | 2026-08-18 | 2026-08-19 | SH-002 | Medium | Planned | 0 | DevOps Lead | Developer setup standardized
SH-024 | StayHub | All | DevOps | CI/CD | Add lint/build/test pipeline | Build frontend in CI | Run backend tests | Use test DB config | None | CI test run | High | 10 | 2026-08-19 | 2026-08-21 | SH-022, SH-023 | Medium | Planned | 0 | DevOps Lead | Automated pipeline
SH-025 | StayHub | All | Deployment | Staging deployment | Deploy frontend/backend/database to staging | Configure frontend env | Deploy backend service | Provision DB | Verify public API | Staging smoke test | Critical | 12 | 2026-08-24 | 2026-08-27 | SH-024 | High | Planned | 0 | DevOps Lead | Working staging environment
SH-026 | StayHub | All | QA | System QA | Run full regression and bug triage | Fix frontend defects | Fix backend defects | Validate data integrity | Retest APIs | Regression/UAT | Critical | 24 | 2026-08-27 | 2026-09-04 | SH-025 | High | Planned | 0 | QA Lead | UAT-ready release candidate
SH-027 | StayHub | All | Performance | Optimization | Optimize dashboard/API/page loads | Add memo/loading optimizations | Optimize queries/indexes | Add DB indexes | Measure key endpoints | Performance test | Medium | 12 | 2026-09-07 | 2026-09-10 | SH-026 | Medium | Planned | 0 | Engineering Manager | Performance acceptable for launch
SH-028 | StayHub | All | Documentation | User and technical docs | Create user workflow notes | API README and env docs | Schema docs | API examples | Doc review | Medium | 10 | 2026-09-10 | 2026-09-14 | SH-026 | Low | Planned | 0 | Technical Writer | Launch documentation
SH-029 | StayHub | All | Release | Production readiness | Prepare release checklist and rollback plan | Final build assets | Production config | Backup plan | Production endpoints | Release validation | Critical | 10 | 2026-09-14 | 2026-09-18 | SH-027, SH-028 | High | Planned | 0 | TPM | Production release plan
SH-030 | StayHub | All | Launch | Go-live | Production deployment and monitoring | Verify deployed UI | Deploy backend | Deploy DB migrations | Smoke API | Post-release smoke test | Critical | 12 | 2026-09-21 | 2026-09-23 | SH-029 | High | Planned | 0 | DevOps Lead | Production go-live

## Timeline_View
Period | Focus
Today - 2026-06-23 | Project audit, backend architecture plan, workbook baseline
Tomorrow - 2026-06-24 | Wire backend routes, normalize DB connection, start schema
Day After Tomorrow - 2026-06-25 | Complete initial DB schema and migrations
Next 7 Days | Backend shell, schema, auth, protected routes, dashboard API foundation
Week 1 | Architecture, database, auth, dashboard integration
Week 2 | Rooms, booking flow, customer CRUD
Week 3 | Check-in/out, housekeeping, maintenance, reviews
Week 4 | Staff, billing, reports, responsive polish
Month 2 | Security, automated testing, CI/CD, staging, QA
Month 3 | Performance, documentation, release hardening, production launch
Expected Completion | 2026-09-23

## Projects_Master
Project Name | Owner | Start Date | Target Date | Current Sprint | Overall Progress % | Frontend % | Backend % | Database % | Testing % | Deployment % | Current Status | Health Status | Expected Completion
StayHub Hospitality Management System | Project Owner | 2026-06-23 | 2026-09-23 | Sprint 1 - Frontend Prototype Expansion | 37 | 68 | 10 | 5 | 0 | 0 | Frontend modules advanced; backend/API pending | Yellow | 2026-09-23

## Daily_Updates
Date | Developer | Project | Sprint | Page | Module | Submodule | Task ID | Task Description | Frontend Status | Backend Status | Database Status | API Status | Testing Status | Priority | Estimated Hours | Actual Hours | Completion % | Current Status | Blockers | Start Date | Target Date | Remarks
2026-06-23 | Codex | StayHub | Sprint 0 | All | Planning | Project audit | SH-001 | Baseline codebase analysis | Done | Done | Done | Done | Manual review done | High | 3 | 3 | 100 | Done | None | 2026-06-23 | 2026-06-23 | Frontend prototype and backend gaps identified
2026-06-23 | Backend Developer | StayHub | Sprint 1 | Backend | Architecture | Server wiring | SH-002 | Wire route modules into Express | Not Started | Planned | Not Started | Planned | Not Started | Critical | 5 | 0 | 0 | Planned | Route imports currently inconsistent | 2026-06-23 | 2026-06-24 | Use config/db and versioned routes
2026-06-24 | Database Engineer | StayHub | Sprint 1 | Database | Schema | Core tables | SH-003 | Create normalized MySQL schema | Not Started | Not Started | Planned | Not Started | Not Started | Critical | 8 | 0 | 0 | Planned | No migrations exist | 2026-06-24 | 2026-06-25 | Add migrations and seed data
2026-06-25 | Full Stack Developer | StayHub | Sprint 1 | Login/Register | Auth | Authentication API | SH-004 | Connect frontend auth to backend | Planned | Planned | Planned | Planned | Not Started | Critical | 8 | 0 | 0 | Planned | Frontend uses localStorage | 2026-06-25 | 2026-06-26 | Replace prototype auth
2026-06-24 | Frontend Developer | StayHub | Sprint 1 | Customers | CRM | Customer UI | SH-011 | Built customer overview, filters, modal form, edit/delete and city/age autofill | In Progress | Not Started | Not Started | Not Started | Manual review pending | High | 6 | 6 | 55 | In Progress | No backend customer API yet | 2026-06-24 | 2026-06-24 | Frontend prototype improved
2026-06-24 | Frontend Developer | StayHub | Sprint 1 | Rooms | Room Management | Filters and gallery | SH-007/SH-008 | Enhanced rooms with type/status/AC/floor filters, gallery images, thumbnails and amenities modal | In Progress | Not Started | Not Started | Not Started | Manual review pending | High | 8 | 8 | 50 | In Progress | No room API persistence yet | 2026-06-24 | 2026-06-24 | Room UI feature depth increased
2026-06-25 | Frontend Developer | StayHub | Sprint 1 | Check-in/out | Front Desk | Local workflow | SH-012/SH-013 | Improved guest list filters, guest modal, check-in form and checkout payment validation | In Progress | Not Started | Not Started | Not Started | Build validation needed | Critical | 5 | 5 | 42 | In Progress | handleSave reference must be fixed | 2026-06-25 | 2026-06-25 | Check-in/out workflow progressed
2026-06-25 | Frontend Developer | StayHub | Sprint 1 | Housekeeping | Operations | Status dashboard | SH-014 | Rebuilt housekeeping status overview with KPI cards, clickable distribution, trend graph, status summary and task list | In Progress | Not Started | Not Started | Not Started | Build validation needed | High | 5 | 5 | 45 | In Progress | Static data only; API pending | 2026-06-25 | 2026-06-25 | Housekeeping UI progressed

## Daily_Task_Planner
Task ID | Today's Tasks | Tomorrow Tasks | Day After Tomorrow Tasks | Estimated Hours | Priority | Dependencies | Status
SH-001 | Complete project audit |  |  | 3 | High | None | Done
SH-002 | Start backend route wiring | Complete backend route wiring |  | 5 | Critical | SH-001 | Planned
SH-003 |  | Design DB schema | Complete DB migrations | 8 | Critical | SH-002 | Planned
SH-004 |  |  | Start secure auth API | 8 | Critical | SH-003 | Planned
SH-006 |  | Document dashboard API requirements | Prepare aggregate queries | Implement first dashboard endpoint | 6 | High | SH-003 | Planned

## Weekly_Roadmap
Week Number | Feature | Page | Module | Owner | Planned Hours | Actual Hours | Dependencies | Target Date | Completion % | Status | Remarks
Week 1 | Architecture, schema, auth, dashboard API | All | Foundation | Full Stack Team | 35 | 3 | None | 2026-06-29 | 8 | In Progress | Current app is prototype-heavy
Week 2 | Rooms, booking flow, customer CRUD | Rooms/Bookings/Customers | Core Operations | Full Stack Team | 44 | 0 | Week 1 | 2026-07-08 | 0 | Planned | Highest user-value sprint
Week 3 | Check-in/out, housekeeping, maintenance, reviews | Operations | Hotel Operations | Full Stack Team | 43 | 0 | Week 2 | 2026-07-18 | 0 | Planned | Requires room/booking status sync
Week 4 | Staff, billing, reports, UX polish | Staff/Finance/Reports | Management | Full Stack Team | 54 | 0 | Week 3 | 2026-08-07 | 0 | Planned | Sidebar items become working pages
Month 2 | Security, tests, CI/CD, staging | All | Quality/DevOps | QA and DevOps | 68 | 0 | Core features | 2026-09-04 | 0 | Planned | Release candidate target
Month 3 | Performance, docs, production launch | All | Release | TPM and DevOps | 44 | 0 | Staging QA | 2026-09-23 | 0 | Planned | Go-live readiness

## Sprint_Tracker
Sprint | Features | Completed | In Progress | Pending | Bugs | Testing Status | Release Readiness | Health Status
Sprint 0 - Discovery | Project audit and workbook baseline | 1 | 0 | 0 | 0 | Manual review only | 10% | Yellow
Sprint 1 - Foundation | Backend wiring, DB schema, auth, dashboard APIs | 0 | 1 | 4 | 0 | Not Started | 20% | Yellow
Sprint 2 - Core Operations | Rooms, bookings, customers | 0 | 0 | 5 | 0 | Not Started | 35% | Yellow
Sprint 3 - Hotel Operations | Check-in/out, housekeeping, maintenance, reviews | 0 | 0 | 4 | 0 | Not Started | 50% | Yellow
Sprint 4 - Management | Staff, billing, reports, UX polish | 0 | 0 | 4 | 0 | Not Started | 65% | Yellow
Sprint 5 - Release Hardening | Security, tests, CI/CD, staging, QA | 0 | 0 | 6 | 0 | Not Started | 85% | Yellow
Sprint 6 - Launch | Performance, docs, production release | 0 | 0 | 4 | 0 | Not Started | 100% | Yellow

## Feature_Tracker
Feature | Frontend | Backend | Database | API | Testing | Deployment | Overall Status | Completion %
Authentication | Prototype | Partial scaffold | Referenced only | Not integrated | None | None | In Progress | 30
Owner Dashboard | Prototype | Partial dashboard controller | Referenced only | Not integrated | None | None | In Progress | 45
Room Management | Enhanced prototype with filters, local CRUD and gallery | Route scaffold only | Referenced only | Not integrated | None | None | In Progress | 58
Booking Management | Incomplete popup | Route scaffold only | Referenced only | Not integrated | None | None | In Progress | 25
Customer Management | Enhanced prototype with filters and modal CRUD | Not implemented | Not implemented | Not implemented | None | None | In Progress | 55
Check-in/out | Enhanced local workflow with filters and checkout validation | Not implemented | Not implemented | Not implemented | None | None | In Progress | 50
Housekeeping | Enhanced static dashboard with status interaction | Not implemented | Not implemented | Not implemented | None | None | In Progress | 48
Maintenance | Static dashboard | Not implemented | Not implemented | Not implemented | None | None | In Progress | 30
Reviews | Prototype modal | Controller empty | Referenced only | Not implemented | None | None | In Progress | 30
Staff Management | Sidebar only | Not implemented | Not implemented | Not implemented | None | None | Not Started | 5
Billing/Reports | Sidebar/dashboard partial | Not implemented | Not implemented | Not implemented | None | None | Not Started | 5
Deployment | Not configured | Not configured | Not configured | Not configured | None | None | Not Started | 0

## Frontend_Tracker
Page | Module | Components | Framework | Status | Completion %
/ | Registration | Register form, validation, Google button UI | React/Vite | Prototype | 65
/login | Login | Login form, password visibility, staff button UI | React/Vite | Prototype | 60
/dashboard | Owner Dashboard | Sidebar, header, KPIs, charts, cards, popups | React/Vite/Recharts | Prototype | 70
/rooms | Room Management | Grid, filters, pagination, add/edit/delete, details modal, gallery, amenities modal | React/Vite | Prototype | 78
Dashboard tab | Customers | Table, stats, add/edit/delete popup | React/Vite | Prototype | 60
Dashboard tab | Customers | Overview cards, filters, customer list, modal add/edit/delete, city/age autofill | React/Vite | Prototype | 75
/checkinout | Check-in/out | Stats, filters, table, guest modal, check-in/out forms, payment validation | React/Vite | Prototype | 70
/housekeeping | Housekeeping | Stats, status distribution, manual trend graph, status popup, room/task lists | React/Vite | Prototype | 68
/maintenance | Maintenance | Request dashboard, technician table, calendar | React/Vite | Prototype | 50
Dashboard popup | Booking | Customer info step only | React/Vite | Incomplete | 25
Dashboard popup | Reviews | Rating summary, tag filters, review cards | React/Vite | Prototype | 60
Sidebar only | Staff/Finance/Reports | Navigation labels | React/Vite | Not Started | 5

## Backend_Tracker
Service | Controller | Business Logic | Middleware | Authentication | Status | Completion %
Express Server | server.js has inline register/login only | Basic plaintext auth flow | CORS/bodyParser only | Weak/Insecure | In Progress | 20
Admin Service | adminController.js | Admin login using bcryptjs | None | Partial scaffold | In Progress | 30
Auth Service | authController.js empty | Missing | Missing | Missing | Not Started | 0
User Service | userRoutes.js has bcrypt flow but not wired | Partial route logic | None | Partial | In Progress | 20
Hotel Service | hotelRoutes.js scaffold, controller empty | Simple CRUD route only | None | Missing | In Progress | 15
Room Service | roomController.js empty | Missing | Missing | Missing | Not Started | 0
Booking Service | bookingRoutes.js scaffold, controller empty | Simple insert/list route only | None | Missing | In Progress | 15
Dashboard Service | dashboardController.js aggregate query | Partial summary query | None | Depends on auth | Partial | 25
Review Service | reviewController.js empty | Missing | Missing | Missing | Not Started | 0
Auth Middleware | authMiddleware.js empty | Missing | Missing | Missing | Not Started | 0

## Database_Tracker
Table | Relationships | Indexes | Migration | Seed Data | Completion %
users | bookings, reviews | email unique needed | Not Created | Not Created | 10
admins | admin auth | email unique needed | Not Created | Not Created | 10
hotels | rooms, bookings, staff | name/location indexes needed | Not Created | Not Created | 10
rooms | hotel, bookings, housekeeping, maintenance | status/type indexes needed | Not Created | Not Created | 10
room_images | rooms | room_id index needed | Not Created | Not Created | 0
amenities | rooms | name unique needed | Not Created | Not Created | 0
bookings | users/customers, hotel, room, payments | checkin/checkout/status indexes needed | Not Created | Not Created | 10
customers | bookings | phone/email indexes needed | Not Created | Not Created | 0
booking_events | bookings | type/date indexes needed | Not Created | Not Created | 0
housekeeping_tasks | rooms, staff | status/date indexes needed | Not Created | Not Created | 0
maintenance_requests | rooms, staff | priority/status indexes needed | Not Created | Not Created | 0
reviews | users/customers, hotel, booking | rating/date indexes needed | Not Created | Not Created | 0
staff | hotel, department | role/status indexes needed | Not Created | Not Created | 0
departments | staff | name unique needed | Not Created | Not Created | 0
attendance | staff | date/staff indexes needed | Not Created | Not Created | 0
invoices | bookings, payments | status/date indexes needed | Not Created | Not Created | 0
payments | invoices | method/status indexes needed | Not Created | Not Created | 0
subscriptions | hotel | plan/status indexes needed | Not Created | Not Created | 0

## API_Tracker
API Name | Endpoint | Method | Integrated | Testing Status | Completion %
Register | /api/auth/register | POST | No | Not Started | 10
Login | /api/auth/login | POST | No | Not Started | 10
Current User | /api/auth/me | GET | No | Not Started | 0
Dashboard Summary | /api/dashboard/summary | GET | No | Not Started | 20
Rooms List | /api/rooms | GET | No | Not Started | 10
Create Room | /api/rooms | POST | No | Not Started | 10
Update Room | /api/rooms/:id | PUT | No | Not Started | 0
Delete Room | /api/rooms/:id | DELETE | No | Not Started | 0
Bookings List | /api/bookings | GET | No | Not Started | 10
Create Booking | /api/bookings | POST | No | Not Started | 10
Customers CRUD | /api/customers | GET/POST/PUT/DELETE | No | Not Started | 0
Check-in | /api/checkins | POST | No | Not Started | 0
Check-out | /api/checkouts | POST | No | Not Started | 0
Housekeeping Tasks | /api/housekeeping | GET/POST/PATCH | No | Not Started | 0
Maintenance Requests | /api/maintenance | GET/POST/PATCH | No | Not Started | 0
Reviews | /api/reviews | GET/POST | No | Not Started | 0
Billing | /api/billing | GET/POST | No | Not Started | 0
Reports | /api/reports/revenue | GET | No | Not Started | 0

## Bug_Tracker
Bug ID | Module | Severity | Assigned To | ETA | Status
BUG-001 | Backend route imports | High | Backend Developer | 2026-06-24 | Open
BUG-002 | Auth security | High | Backend Developer | 2026-06-26 | Open
BUG-003 | Frontend/backend auth mismatch | High | Full Stack Developer | 2026-06-26 | Open
BUG-004 | BookingPopup onSave not used because component does not accept onSave | Medium | Frontend Developer | 2026-07-04 | Open
BUG-005 | Booking wizard only has step 1 implemented | High | Frontend Developer | 2026-07-04 | Open
BUG-006 | Encoding issues display rupee/check icons incorrectly | Medium | Frontend Developer | 2026-08-07 | Open
BUG-007 | Recharts dependency missing from frontend package.json but used in source | Medium | Frontend Developer | 2026-06-24 | Open
BUG-008 | No database migrations or seed data | High | Database Engineer | 2026-06-25 | Open
BUG-009 | No automated tests | High | QA Lead | 2026-08-18 | Open
BUG-010 | BookingPopup runtime behavior needs verification after commented implementation was found | Medium | Frontend Developer | 2026-06-26 | Open
BUG-011 | CheckInOut.jsx references undefined handleSave in edit modal | High | Frontend Developer | 2026-06-26 | Open
BUG-012 | Several UI files still show broken encoded rupee/icon characters | Medium | Frontend Developer | 2026-06-27 | Open

## Testing_Tracker
Feature | Unit Test | Integration Test | Manual Test | UAT | Status
Authentication | Not Started | Not Started | Needed | Not Started | Open
Dashboard | Not Started | Not Started | Needed | Not Started | Open
Rooms | Not Started | Not Started | Needed | Not Started | Open
Bookings | Not Started | Not Started | Needed | Not Started | Open
Customers | Not Started | Not Started | Needed | Not Started | Open
Check-in/out | Not Started | Not Started | Needed | Not Started | Open
Housekeeping | Not Started | Not Started | Needed | Not Started | Open
Maintenance | Not Started | Not Started | Needed | Not Started | Open
Billing/Reports | Not Started | Not Started | Needed | Not Started | Open
Security | Not Started | Not Started | Needed | Not Started | Open
Deployment | Not Started | Not Started | Needed | Not Started | Open

## Deployment_Tracker
Environment | Frontend Version | Backend Version | Database Version | Status
Local Dev | 0.0.0 | 1.0.0 | Manual local MySQL reference | Partial
Test | Not Created | Not Created | Not Created | Not Started
Staging | Not Created | Not Created | Not Created | Not Started
Production | Not Created | Not Created | Not Created | Not Started

## Risks_And_Blockers
Risk Type | Description | Severity | Owner | Mitigation Plan | Status
Architecture | Backend server does not wire scaffolded route modules | High | Backend Developer | Refactor server with versioned API router | Open
Security | Plaintext password flow exists in current server | High | Backend Developer | Use bcryptjs, JWT, validation, rate limiting | Open
Database | No schema/migration files are present | High | Database Engineer | Create migrations and seed strategy | Open
Integration | Frontend uses localStorage/static state instead of APIs | High | Full Stack Developer | Introduce API service and connect module by module | Open
Quality | No automated tests or CI pipeline | High | QA Lead | Add focused API and UI tests before release | Open
Delivery | Many modules are prototype-only | Medium | Engineering Manager | Prioritize rooms/bookings/auth before staff/finance | Open
UX | Encoding issues show broken symbols in UI | Medium | Frontend Developer | Normalize file encoding and replace broken characters | Open
Dependency | Recharts used but not listed in frontend dependencies | Medium | Frontend Developer | Add dependency to frontend package | Open
Deployment | No staging or production environment defined | High | DevOps Lead | Create env docs, CI, staging deployment | Open

## Team_Productivity
Developer | Tasks Completed | Hours Worked | Productivity Score | Remarks
Codex | 1 | 3 | 90 | Completed analysis and project workbook baseline
Frontend Developer | 0 | 0 | 0 | Ready for Sprint 1 UI/API integration tasks
Backend Developer | 0 | 0 | 0 | Ready for server wiring and auth tasks
Database Engineer | 0 | 0 | 0 | Ready for schema and migration tasks
QA Lead | 0 | 0 | 0 | Testing framework not started
DevOps Lead | 0 | 0 | 0 | Deployment pipeline not started
Project Owner | 0 | 0 | 0 | Needs priorities and acceptance criteria confirmation

## Daily_Report
Metric | Report
Date | 2026-06-25
Completed Tasks | 2-day frontend progress added for Customers, Rooms, Check-in/out, Housekeeping
Tasks In Progress | SH-007, SH-008, SH-011, SH-012, SH-013, SH-014
Pending Tasks | Backend APIs, database schema, auth integration, tests, deployment
Blockers | No DB migrations, backend routes not wired, frontend still uses static/local state, BookingPopup runtime needs verification, CheckInOut has undefined handleSave when edit mode saves
Bug Fixes | No verified bug fixes; new bugs BUG-010 to BUG-012 logged
Hours Worked | 24 estimated frontend hours across 2026-06-24 to 2026-06-25
Today's Progress % | 45% for active frontend module updates
Overall Project % | 37%
Tomorrow's Deliverables | Fix BookingPopup export, fix CheckInOut handleSave, run build, start backend route/API integration
Health Status | Yellow

## Weekly_Report
Field | Report
Week 1 Summary | Foundation sprint should complete server wiring, schema, auth, protected routes, and dashboard summary API
Week 2 Summary | Core operations sprint should complete rooms, booking flow, and customers
Completed Features | Frontend prototypes for dashboard, rooms, customers, check-in/out, housekeeping, maintenance, reviews
Pending Features | API integration, database persistence, staff, billing, reports, deployment
Delays | Backend and database are behind frontend prototype maturity
Dependencies | MySQL schema is dependency for most backend work; auth is dependency for protected workflows
Risks | Security/auth mismatch, no tests, no deployment pipeline
Testing Status | Not started
Overall Completion % | 37%
Expected Completion Date | 2026-09-23
Health Status | Yellow

## Release_Report
Area | Status
Frontend Completion % | 68
Backend Completion % | 10
Database Completion % | 5
API Completion % | 5
Testing Completion % | 0
Deployment Completion % | 0
Security Status | Not release-ready; plaintext auth and missing middleware must be fixed
Performance Optimization | Not started
CI/CD Status | Not started
Known Issues | Backend not wired, no migrations, static frontend data, incomplete booking wizard, no tests
Release Readiness % | 18
Confidence Level % | 38
Ready For Deployment | NO

## Continuous_Memory
Rule | Current Baseline
Roadmap Persistence | Update this file on each progress update; do not recreate from scratch
Progress Updates | Move task statuses from Planned to In Progress to Done and adjust completion percentages
Daily Planning | Refresh Sheet 2 and Sheet 3 each workday
Sprint Health | Update Sheet 5 after every completed task or blocker
Release Readiness | Update Step 6 after tests, security, CI/CD, and staging progress
Overall Progress Baseline | Updated to 37% on 2026-06-25 after 2-day frontend progress